# Customer Acquisition Engine

## Detailed 180-Day Growth Plan

### From 0 → 10,000 Users → $10k MRR

# Objective

За первые 180 дней:

- получить первые 10,000 пользователей;

- достичь 1,000 платящих подписчиков;

- выйти на $10,000 MRR;

- найти Product-Market Fit;

- доказать retention.

# Core Growth Philosophy

Большинство стартапов пытаются покупать пользователей.

Мы будем создавать:

### Emotional Virality

Потому что родители делятся эмоциями намного чаще, чем технологиями.

# The Main Growth Loop

Parent sees video

↓

Creates story

↓

Child reacts emotionally

↓

Parent shares

↓

New parents arrive

↓

Repeat

# First 30 Days

## Foundation Phase

# Goal

Получить первые:

### 100 пользователей

без рекламы.

# Main KPI

Не регистрации.

### Story Completion Rate

Цель:

70%+

# Week 1

## Create TikTok Account

Название должно быть максимально понятным.

Примеры:

- StoryForMyKid

- BedtimeMagic

- LittleHeroStories

- MoonStoryKids

# Create Content Library

Сразу подготовить:

### 100 видео

до запуска.

# Video Template 1

Fear Of Darkness

Hook:

“My son was afraid to sleep alone.”

Middle:

“We created a story where he became a space explorer.”

Ending:

“He asked for part 2 the next night.”

Duration:

15–25 sec

# Video Template 2

Child Anxiety

Hook:

“If your child worries all the time…”

Middle:

“Try turning them into the hero.”

Ending:

“Watch what happens.”

# Video Template 3

Story Reveal

Показываем:

- картинки;

- персонажа;

- озвучку.

# Week 2

Start Posting

### 5 videos/day

Goal:

Получить первые:

10,000 views

# Metrics

View Rate

Watch Time

Comments

Shares

# Week 3

Launch Landing Page

Headline:

### Personalized bedtime stories that help kids feel stronger, calmer and happier.

CTA:

### Create Free Story

# Collect Emails

Даже если продукт еще не готов.

Goal:

100 emails

# Week 4

Open Beta

Invite:

100 families

Free access.

Collect:

- feedback;

- testimonials;

- videos.

# Month 2

## Validation Phase

# Goal

500 users

# KPI

Stories Per Family Per Week

Target:

2+

# Content Volume

Increase:

### 10 videos/day

# Daily Content Mix

3 emotional stories

2 child psychology videos

2 product demos

2 parent problem videos

1 experimental viral video

# Viral Angles

“My daughter became the hero of her own story”

“AI helped my son sleep”

“The story made him cry”

“He keeps asking for the dragon”

# Start Instagram

Post:

2–3 Reels/day

Stories:

daily

# Build Trust

Show:

- parents;

- children;

- reactions.

# Month 3

## First Growth Engine

# Goal

1,500 users

# Introduce Subscription

Free:

3 stories

Paid:

$9.99/month

# KPI

Conversion:

10%

# Email Automation

Day 0

First story

Day 1

Second story

Day 3

New emotional theme

Day 5

Success story

Day 7

Upgrade offer

# SEO Starts

Publish:

### 10 pages/day

Topics:

Stories for:

- anxiety

- darkness

- school

- confidence

- friendship

# Example URLs

/fear-of-darkness-story

/anxiety-bedtime-story

/school-anxiety-story

# Month 4

## Retention Optimization

# Goal

3,000 users

# Main KPI

Stories Per Week

Target:

3+

# Introduce Story Series

Huge retention feature.

Example:

Leo Universe

Episode 1

Moon Dragon

Episode 2

Dragon Returns

Episode 3

Space Forest

# Introduce Story Streak

3 nights in a row

7 nights in a row

14 nights

Creates habit.

# Introduce Weekly Adventures

Every Sunday:

new episode.

# Month 5

## Scale Phase

# Goal

5,000 users

# Launch Influencer Program

Target:

100 parenting creators

Size:

5k–50k followers

Offer:

Free lifetime access.

# Goal

20 influencer posts/month

# Influencer Script

“My son became the main character of his own bedtime story.”

# Launch Referral Program

Invite friend

↓

Get free stories

↓

Both receive bonus

# Referral Goal

20% of new users

# Month 6

## Revenue Push

# Goal

10,000 users

# Conversion

10%

Paid Users:

1,000

MRR:

$10,000

# Introduce Premium

$19.99/month

Includes:

- family voice;

- advanced story memory;

- premium story packs.

# Daily Operating Dashboard

Every morning review:

New Users

Stories Generated

Stories Completed

Stories Per Family

Conversion

MRR

Churn

Retention

# Content Machine Blueprint

# Daily Production

10 TikToks

3 Reels

1 Blog Article

10 SEO Pages

1 Email

# Weekly Production

70 TikToks

21 Reels

7 Articles

70 SEO Pages

# Emotional Content Database

Create library:

Fear Of Darkness

Anxiety

Divorce

Bullying

Confidence

School

Friendship

Loneliness

Anger

Sleep

Each category:

50+ content ideas.

# Viral Hooks Database

“My son couldn’t sleep alone.”

“This AI story changed bedtime.”

“I wasn’t expecting this reaction.”

“He asked for the dragon again.”

“The story felt like therapy.”

“Parents need to see this.”

# Parent Psychology Strategy

Never sell AI.

Never sell features.

Never sell stories.

Sell:

Safety

Connection

Confidence

Sleep

Love

# Growth Bottlenecks

Stage 1

No traffic

↓

Fix content

Stage 2

Traffic but no signups

↓

Fix landing page

Stage 3

Signups but no retention

↓

Fix stories

Stage 4

Retention but no subscription

↓

Fix pricing

# PMF Signals

Strong signals:

Parents create 3+ stories/week

Parents share stories

Children ask for new stories

Retention > 40% after 30 days

Organic referrals appear

# Red Flags

Users create:

1 story

and disappear.

Parents say:

“Cool technology.”

Instead of:

“My child loves it.”

Low repeat usage.

# The Most Important Metric In The Entire Company

Not:

MRR

Not:

Users

Not:

Traffic

The metric that predicts everything:

### Average Stories Per Family Per Week

Because if families return multiple times every week:

Retention grows

↓

LTV grows

↓

MRR grows

↓

Business survives

# Final Mission

Создать продукт, который ребенок будет просить каждый вечер.

Потому что в этот момент маркетинг перестает быть рекламой.

И превращается в привычку семьи.